## Copy of Print ready 1
Founder Name - “I commit to executing this roadmap with discipline.” Signature:
Start Date - |  | 🚀 THE BRAND BUILDING CLIMB
Target Launch Date -
Status | Task/Step | Capital Requirement | PHASE 1 - Research & Product Finalisation | [7 empty] | PHASE 2 - Supplier & Operatioal Setup |  |  |  | PHASE 3 - Amazon Setup |  | PHASE 4 - Branding & Launch
Date
|  |  | Week 0 | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20
FALSE | Foundational Clarity Necessary for E-com Biz | 🔹 Low | bar: Date Week 0
FALSE | Market Scanning & Product Discovery | bar: Date Week 1 to Date Week 2
FALSE | Product Shortlisting Using 21-Point Framework | bar: Date Week 3 to Date Week 4
FALSE | Product Innovation / Strategy | bar: Date Week 3 to Date Week 4
FALSE | Business Incorporation (USA, EIN) | 🟡 Medium | bar: Date Week 5 to Date Week 7
FALSE | ODI Compliance (for US Biz Entity) | bar: Date Week 5
FALSE | Deep Validation to Select Final Options | bar: Date Week 5
FALSE | Unit Economics & Profit Modelling | bar: Date Week 6
FALSE | Supplier Discovery | bar: Date Week 6 to Date Week 7
FALSE | Final Product Selection | bar: Date Week 7
✔ PHASE 1 Complete - Product Locked
FALSE | Shortlisting Suppliers | bar: Date Week 8
FALSE | Placing Order for Samples | 🔹 Low | bar: Date Week 9
FALSE | Sample Shipping | 🔹 Low | bar: Date Week 9
FALSE | Naming Your Brand | bar: Date Week 9
FALSE | Trademark | 🟡 Medium | bar: Date Week 10
FALSE | Domain Acquisition | 🔹 Very Low | bar: Date Week 9
FALSE | Amazon Account Setup | 🔹 Very Low | bar: Date Week 9
FALSE | Sample Review & Supplier Lock | bar: Date Week 10 to Date Week 11
✔ PHASE 2 Complete - Supplier Confirmed
FALSE | UPC Procurement / Barcodes (Rough + GS1) | 🔹 Very Low | bar: Date Week 10
FALSE | Brand Registry on Amazon | bar: Date Week 10
FALSE | Rough Amazon Listing | bar: Date Week 11
FALSE | Final Amazon Listing with GS1 Barcodes | bar: Date Week 11
FALSE | Certification / Patents Review (CE, FDA, REACH, ISO 9001) | bar: Date Week 10 to Date Week 11
FALSE | Product Compliance & Lab Testing | 🟡 Medium | bar: Date Week 11 to Date Week 13
FALSE | Shipping Plan Creation | bar: Date Week 10
FALSE | Brand Identity & Packaging Design | 🟡 Medium | bar: Date Week 11 to Date Week 13
✔ PHASE 3 Complete - Inventory Shipped
FALSE | Shipping Quotation (90% Accuracy) | 🔴 High | bar: Date Week 14 to Date Week 17
FALSE | Inspection & Shipping | 🔴 High | bar: Date Week 18 to Date Week 20
FALSE | Product Photography | 🟡 Medium | bar: Date Week 15 to Date Week 16
FALSE | Amazon Listing SEO | 🔹 Low | bar: Date Week 18
FALSE | Amazon Listing Design | 🟡 Medium | bar: Date Week 17 to Date Week 19
✔ PHASE 4 Complete - Brand Live
NOTE: This roadmap is a guide. Execution decides the outcome. Copyright Protected